Internal Assessment Resource

Mathematics and Statistics Level 3

This resource supports assessment against: Achievement Standard 91576 Use critical path analysis in solving problems

Resource title: Project planning

2 credits

This resource: Clarifies the requirements of the standard Supports good assessment practice Should be subjected to the school’s usual assessment quality assurance process Should be modified to make the context relevant to students in their school environment and ensure that submitted evidence is authentic

| Date version published by Ministry of Education | December 2012 To support internal assessment from 2013 |
| --- | --- |
| Quality assurance status | These materials have been quality assured by NZQA. NZQA Approved number A-A-12-2012-91576-01-6200 |
| Authenticity of evidence | Teachers must manage authenticity for any assessment from a public source, because students may have access to the assessment schedule or student exemplar material. Using this assessment resource without modification may mean that students’ work is not authentic. The teacher may need to change figures, measurements or data sources or set a different context or topic to be investigated or a different text to read or perform. |

Internal Assessment Resource

Achievement Standard Mathematics and Statistics 91576:

Use critical path analysis in solving problems

# Resource Reference: Mathematics and Statistics 3.4B

# Resource Title: Project planning

# Credits: 2

# Teacher guidelines

The following guidelines are designed to ensure that teachers can carry out valid and consistent assessment using this internal assessment resource.

Teachers need to be very familiar with the outcome being assessed by Achievement Standard Mathematics and Statistics 91576. The achievement criteria and the explanatory notes contain information, definitions, and requirements that are crucial when interpreting the standard and assessing students against it.

# Context/setting

This activity requires students to write a report making recommendations based on a critical path analysis of a project. Students are required to develop and schedule a project of their own choice.

# Conditions

This activity should be conducted over a number of sessions. Students can work in a group to develop the project brief and to identify necessary tasks and the order in which tasks need to be completed. Ensure that the precedence table is non-trivial and provide time for students to correct or improve their table before beginning the analysis and reporting phase.

Authenticity of student evidence needs to be assured. If group work is involved in developing the project brief and identifying the tasks and creating a precedence table, the teacher needs to be assured that all students have actively contributed. This may be through direct observation or by questioning students about the process.

The remainder of the task must be completely individually.

Students may use appropriate technology.

Resource requirements

None.

# Additional Information

For this task you need to ensure that the students’ precedence tables are sufficiently difficult to enable evidence to be provided for all grades of achievement.

Teachers could adapt this activity to make it compatible with another Achievement Standard, for example, Achievement Standard Technology 3.2: Undertake project management to support technological practice.

Internal Assessment Resource

Achievement Standard Mathematics and Statistics 91576:

Use critical path analysis in solving problems

# Resource Reference: Mathematics and Statistics 3.4B

# Resource Title: Project planning

# Credits: 2

| Achievement | Achievement with Merit | Achievement with Excellence |
| --- | --- | --- |
| Use critical path analysis in solving problems. | Use critical path analysis, with relational thinking, in solving problems. | Use critical path analysis, with extended abstract thinking, in solving problems. |

Student instructions

# Introduction

This activity requires you to develop a project schedule for a project of your choice and to write a report showing how the project will be managed.

The quality of your reasoning and your ability to identify the impact of unexpected delays will determine the overall grade.

You can work in a group to develop the project brief and to identify necessary tasks and the sequence in which tasks must be completed. The remainder of the activity must be completely individually.

Before you proceed with the task you must ensure your teacher has checked that your precedence table is of sufficient difficulty.

You have <<teacher to insert time and conditions here>> to complete this activity.

# Task

This task requires you to use a critical path analysis to plan a project of your choice and to write a report showing how the project will be managed.

Choose a project. This project could be an event, for example, planning the school ball or a meal for a group of friends, or a product, for example, making a pair of trousers. The project should have at least eight individual tasks. Ensure that some of the tasks can be worked on simultaneously.

Write a brief for the project.

Create a list of the separate tasks for your project including:

the length of time you expect each task to take

a precedence table for the tasks in the project.

Give the critical path and the minimum completion time for the project.

Give the start and finish times for each task.

Recommend appropriate review points in the project so that you can check progress.

Discuss the implications of any delays in completing one or more tasks within the project.

# Assessment schedule: Mathematics and Statistics 91576 Project planning

Teacher note: You will need to adapt this assessment schedule to include examples of the types of responses that can be expected.

| Evidence/Judgements for Achievement | Evidence/Judgements for Achievement with Merit | Evidence/Judgements for Achievement with Excellence |
| --- | --- | --- |
| The student has used critical path analysis in solving problems. This involves: selecting and using methods, demonstrating knowledge of concepts and terms communicating using appropriate representations Example of possible student response: The student has: drawn a correctly labelled network diagram that includes all tasks in the precedence table established the critical path and minimum amount of time required to complete the project. The examples above are indicative of the evidence that is required. | The student has used critical path analysis, with relational thinking in solving problems. This involves one or more of: selecting and carrying out a logical sequence of steps connecting different concepts or representations demonstrating understanding of concepts forming and using a model The student has also related their findings to a context, or communicated thinking using appropriate mathematical statements. Example of possible student response: The student has drawn a correctly labelled network diagram that includes all tasks in the precedence table. They have used their diagram to: do a forward/backward scan to establish start and finish times establish the critical path and its length recommend appropriate review points to check progress discuss the impact of a task on the critical path taking longer to complete than the allocated time. The examples above are indicative of the evidence that is required. | The student has used critical path analysis, with extended abstract thinking, in solving problems. This involves one or more of: devising a strategy to investigate or solve a problem identifying relevant concepts in context developing a chain of logical reasoning forming a generalisation The student has also used correct mathematical statements, or communicated mathematical insight. Example of possible student response: The student has established the critical path, found the minimum time, discussed start/finish times, and recommended appropriate review points. They have discussed the possibility of tasks taking longer than the allocated time to complete and also the impact of delays to other tasks on the critical path, minimum time, start/finish times, and placement of review points. Discussion on float times with respect to project requirements has been included. The examples above are indicative of the evidence that is required. |

Final grades will be decided using professional judgement based on a holistic examination of the evidence provided against the criteria in the Achievement Standard.

# Text boxes

NZQA Approved